## Network Diagram
ASSIGNMENT 3 – QUESTION 1
| Activity | Starting Node | Ending Node | Pessimistic Duration | Optimistic Duration | Most Likely Duration | Duration of Activities
| A | 1 | 3 | 6 | 2 | 4 | 4
| B | 2 | 3 | 12 | 4 | 5 | 6
| C | 3 | 4 | 15 | 3 | 6 | 7
| D | 3 | 5 | 12 | 4 | 5 | 6
| E | 3 | 6 | 13 | 3 | 5 | 6
| F | 4 | 7 | 20 | 2 | 8 | 9
| G | 5 | 7 | 15 | 5 | 7 | 8
| H | 6 | 8 | 14 | 2 | 8 | 8
| I | 8 | 7 | 13 | 1 | 4 | 5
| 1 |  |  |  | 4
7
|  |  | 3 |  | 5
| 2 |  |  |  | 6 |  | 8
CRITICAL PATH : BEHI = 25
A=4
B=6
C=7
D=6
E=6
F=9
G=8
H=8
I=5

## Earned Value Analysis
Activity | Duration | START DATE | END DATE | Predecessor | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | %COMPLETE | Budget | Cost to Date (AC) | PV | EV | Duration
A | 4 | 2023-12-01 | 2023-12-06 | [36 empty] | 100 | 400 | 600 | 400 | 400 | 25 | bar: F to W; S to S; S to S; S to S
B | 6 | 2019-11-19 | 2019-11-21 | 2 | [35 empty] | 100 | 200 | 150 | 200 | 200 | bar: F to S; S to S; S to S
C | 7 | 2019-11-19 | 2019-11-22 | 2 | [35 empty] | 100 | 300 | 350 | 300 | 300 | bar: S to T; S to S
D | 6 | 2019-11-19 | 2019-11-20 | 2 | [35 empty] | 100 | 600 | 525 | 600 | 600 | bar: S to M; S to S
E | 6 | 2019-11-25 | 2019-11-25 | 3,4 | [35 empty] | 100 | 450 | 450 | 450 | 450 | bar: S to M; S to S
F | 9 | 2019-11-21 | 2019-11-25 | 5 | [35 empty] | 70 | 900 | 450 | 100 | 630 | bar: S to S; S to S; W to M
G | 8 | 2019-11-26 | 2019-11-27 | 6 | [35 empty] | 60 | 1000 | 300 | 250 | 600 | bar: S to S; S to S; T to T
H | 8 | 2019-11-26 | 2019-11-28 | 7 | [35 empty] | NOT STARTED | 800 | 0 | 200 | 0 | bar: S to S; S to S; T to T
I | 5 | [38 empty] | NOT STARTED | 500 | 0 | 0 | 0 | bar: S to S; S to S; S to S; F to T
[5 empty] | T: 25 |  | 5150 | 2825 | 2500 | 3180
[41 empty] | CV | 355
[41 empty] | SV | 680
[41 empty] | SPI | 1.272
[41 empty] | CPI | 1.1257
[41 empty] | EAC | 4575.0786 | -574.9214 | Need more to Complete
[41 empty] | Forecasted Duration | 19.6541 | -5.3459
A) TOTAL PLANNED VALUE = $2175
B) TOTAL EARNED VALUE = $3180
C) TOTAL ACTUAL COST = $2825
D) CPI > 1 AND SPI > 1 = Under Budget and Ahead of Schedule
E) EAC = $4575
F) FORECASTED DURATION = 19.6540 (~ - 5.34 DAYS)